## Product Backlog User Stories
Key | As a ... | I want to... | so that .... | Proirity | Story Point | Status | Sprint
MAPP-US1 | Student | have a personalized learning path that targets my weaknesses and provides practices problems that are relevant, | my understanding improves and the gaps of my knowlegde are filled. | Must Have | 13 | In Progress | Sprint 2
MAPP-US2 | Student | have practice problems that are interactive and engages me, | I can stay motivated and see improvement in my problem solving skills. | Must Have | 8 | Not Started Yet | Sprint 3
MAPP-US3 | Student | have quick access to explanations and personalized, scaffolded help for challenging problems, | I have the confidence to tackle challenging problems and gain a deeper understanding the concept. | Must Have | 5 | Not Started Yet | Sprint 3
MAPP-US4 | Student | have an app that allows me to access my learning path profile that includes all my current and saved progress, | I can practice my math lessons anytime and anywhere. | Should Have | 3 | Not Started Yet | Sprint 3
MAPP-US5 | Student | have an app that integrates materials for my textbook and/or online platforms, | I can bounce form one learning tool to another within the app. | Could Have | 2 | Not Started Yet | Sprint 3
MAPP-US6 | Student | have an app that provides specific practice problems and exams that aligns with the SAT and Regents exams format, | I can place my focus on the content that I need to work on to fully prepare for the exams and gain confidence for them. | Could Have | 1 | Not Started Yet | Sprint 3
MAPP-US7 | Teacher | have a platform that identifies the subject area of the problem to incorporate a variety of engaging and differentiated learning resources, | I can cater to my students needs and personalized their learning goals. | Must Have | 13 | In Progress | Sprint 2
MAPP-US8 | Teacher | have a platform that creates personalized learning paths for my students based on how they perform and grasp the content, | they can work on their weaknesses and increase their learning potential. | Must Have | 8 | Not Started Yet | Sprint 3
MAPP-US9 | Teacher | have computerized tool that can monitor my students' progress in real-time and pinpoints the areas where my students' need extra support, | intervene in sooner than later in an effective way. | Must Have | 5 | Not Started Yet | Sprint 3
MAPP-US10 | Teacher | have resources and support that will help understand how to intergrate this platform into my classroom, | I can use it effectively in my lesson plans and teaching practices. | Should Have | 3 | Not Started Yet | Sprint 3
MAPP-US11 | Teacher | have extra tools that will allow my students to access more practice problems and personalized learning paths outside of the classroom, | they can reinforce what they learned in class or get extra support and do this at their own pace. | Should Have | 2 | Not Started Yet | Sprint 3
MAPP-US12 | Teacher | be able to access resources that is aligned with Algebra 2 and Precalculus tests, | I can prepare my students fully for these exams. | Could Have | 1 | Not Started Yet | Sprint 3
MAPP-US13 | Tutor | access diagnotic assessments that pinpoints the student's area of difficulty, | I can create a personalized tutor session and support. | Must Have | 13 | In Progress | Sprint 2
MAPP-US14 | Tutor | I want to access learning resources that are engaging and diverse, | explanations and practice problems can be tailored to the student's needs | Must Have | 8 | In Progress | Sprint 2
MAPP-US15 | Tutor | I want to be able to track the student's progress with homeworks and practice problems, | I can determine the area of concern and provide additional support. | Must Have | 5 | Not Started Yet | Sprint 3
MAPP-US16 | Tutor | I want to tools that give students the chance to communicate with their teachers to asks questions and/or receive clarifications on certain topics during tutor sessions, | the student can take ownenshp of their learning | Should Have | 3 | Not Started Yet | Sprint 3
MAPP-US17 | Tutor | I want to have access to interactive learning activities, | I can increase the engagement and retention of the student. | Could Have | 2 | Not Started Yet | Sprint 3
Placeholder | Placeholder |  |  | Placeholder | Placeholder | Placeholder | Placeholder